Bembridge PC costs proposal for processing and analysis of Housing Needs Survey by Rural Housing Enabler (RHE)

Set up spreadsheet– 2 hours

2 x £20 = £40

Processing time

Current surveys: 12 minutes per survey X 500 = 100 hours

Assuming further 50 surveys: 12 minutes per survey x 50 = 10 hours

Total 550 surveys

110 x £20 per hour = £2200

Analysis and write up – 20 hours

20 x £20 = £400

Amendments to / Presentation of report – 14 hours

14 x £20 = £280

----------------

Total estimated cost = £2920

-----------------

Contribution from Rural Housing Enabler budget - £1000

Rural Housing Enabler time of 7 hours - £280

------------------

Proposed fee = £1640

-----------------

Further cost to be added for every 20 surveys would be £4

-------------

The above proposal is based on the following milestones being met:

- Bembridge PC to provide current Survey Monkey data by 2/1/24

- BPC to provide RHE with all further Surveys by 22/1/24

- RHE to provide draft data summary by 9/2/24

- RHE to attend PC meeting on 21/2/24 to present

- RHE to attend BPC meeting on 21/2/24 to present results and analysis to date

- RHE to send final draft report to BPC by 8/3/24